## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
EES Tasks
| EES_Firmware_Task_Tracker | EES Tasks - EES_Firmware_Task_T
Version Control
| Table 1 | Version Control

## EES Tasks - EES_Firmware_Task_T
EES_Firmware_Task_Tracker
ID | Issue | Description | EES Response | Conclusion 21.05.25/30.05.25/09.06.25/12.06.25/17.06.25/01.07.25 | EES Response 29.05.25/05.06.25/10.06.25/17.06.25 | Assigned To | Priority | Status | Firmware Version | Tested Version | Notes
1 | Overspeed Alert UI Stuck in Red | After overspeeding, the UI goes red but does not revert to normal once speed is reduced. | The background color of the UI is controlled by the APP. Pls check APP(ID:0x01,[36]) | IPI concluded that it is not the app at fault, it is still required for EES to investigate in FW of product. IPI/Rushabh will send commands/simuation to prove the scenario is product FW regarding "clear" instruction. 30.05.25: 1. This appears to be a bug. I have verified it in version 0.1.4—under certain conditions, even after sending the correct command, the UI does not revert to the normal state. 09.06.25 Okay let us check this on our side. Can we get access to see firmware logs? That will help us to debug the same way you do. 12.06.25 Verified this issue, it is fixed now | 提供的报文检查正确，检查软件是否为最新0.1.4。 设备软件0.1.4，Pure_Go_debugV1.0(10)验证，功能正常 The provided message has been checked and found to be correct. Check if the software is the latest version 0.1.4. The device software is 0.1.4, Pure_Go_debugV1.0(10). The verification shows that the function is normal. 05.06.25[问题] 使用“Road Angel”实测，报文中数据长度异常，可能导致数据缺失 [bug] The data length in the message is abnormal when tested with "Road Angel", which may lead to data loss. 10.06.25 设备无日志功能，EES是通过飞线引出蓝牙模块两个通讯线，通过串口模块监控通讯链路 The device has no logging function. EES connects two communication lines of the Bluetooth module through a flying lead and monitors the communication link through a serial port module.
2 | Device UI Unresponsive After Connection | Occasionally, on Bluetooth connection, the device UI does not update even though alerts and sounds are working. The device may become unresponsive. | Need a more detailed description or illustration, it might be that the priority of pairing this mobile phone is lower than that of the currently connected one. | IPI concluded that the scenario is not with regards to mobile connection priority. IPI/Rushabh try to replicate and send video to EES. To be investigated by EES. 30.05.25 This issue is occurring with our app as well. During testing, we did not perform an OTA update. On each connection, the device is expected to display the UI and begin updating speed and other components. Can you please confirm if this behavior has been addressed in the firmware modifications made by EES? 09.06.25 We will test once we will receive new firmware 12.06.25 Testing 01.07.25 Verified this issue, it is fixed now | 这是测试APP的bug，例如使用手机OTA后，设备重启，测试APP会自动重连设备，但未发送连接指令，会出现该现象 措施：固件调整 建议：正式APP请在OTA后主动断开连接 This is a bug in the testing APP. For instance, after using the mobile OTA function, the device restarts. The testing APP will automatically reconnect to the device, but it fails to send the connection command. This is the phenomenon that occurs. Measures: EES modified firmware. Suggestion: For official apps, please actively disconnect the connection after the OTA process. 05.06.25[问题] 更新V00.1.5 准备两台设备，使用APP测试（6/10前完成） [bug] 1. Updated FW to V00.1.5 2. Prepare two devices and use the APP for testing (finish by 6.10) 10.06.25 Updated FW to V00.1.6 17.06.25 Pls update testing result.
3 | Average Speed Alert Inconsistency | Average speed alerts do not always trigger, and the average speed value is missing from the alert display. | The average speed is not used in the current UI. | IPI concluded the UI/FW is to be updated to show average speed when travelling through average speed cameras. EES to check he has full UI/screenshots, Rushabh will resend UI/figma full files 30.05.25 A detailed description of this behavior has been provided under Task 4. Kindly review it for further clarification 09.06.25 We will test once we will receive new firmware. 12.06.25 Verified this issue, it is fixed now | 提供图片中所显示的数据参数，为AlertDistance(ID:0x01,[31~34])， 请确认是否从AlertDistance修改为AverageSpeed Provide the data parameters shown in the picture, namely AlertDistance (ID: 0x01, [31~34]). Please confirm whether to change it from AlertDistance to AverageSpeed. 05.06.25[新需求] 更新V00.1.6 在当前UI基础上调整，无平均速度图片，修改文本（将"METERS"修改为"AVERAGE"） [New requirement] 1. Updated FW to V00.1.6 2. Make adjustments on the current UI. Remove the average speed image and modify the text (change "METERS" to "AVERAGE").
4 | Sound Button Does Not Cycle | Sound button press does not cycle through available options as expected. | The latest firmware has added this function. Please confirm if it is the latest version firmware. | IPI/Rushabh will update new firmware 22 May & test/confirm. 30.05.25 Can you please confirm if this behavior has been addressed in the firmware modifications made by EES? 09.06.25 We will test once we will receive new firmware. 12.06.25 Verified this issue, it is fixed now | “轻触”触发声音调整，“长按”触发关闭 措施：固件调整 注意：固件将延长判断，但该问题与使用习惯相关 "A light touch" activates the sound adjustment, while "a long press" triggers the shutdown. Measures: EES modified firmware. Note: The firmware will increase the processing time, but this issue is related to usage habits. 05.06.25[问题] 更新V00.1.5 调整触发判断 [bug] 1. Updated FW to V00.1.5 2. Adjust the trigger condition
5 | Implement Latest UI Changes from Figma | Rushabh to make a list of all changes. Firmware should reflect updated UI. | The corresponding agreement needs to be updated. | As point 3. 30.05.25 This is necessary to notify the user when a new firmware version is available. It is also required to guide the user on how to update the firmware through the app. The app already sends information to the device when GPS is unavailable; the device only needs to update the UI accordingly. EES 05.06.25 [new requirement, not recommend] 1. Add upgrade prompt to UI (estimated 6 days): It is necessary to clearly specify which button to press to enter the "upgrade prompt" interface, provide the upgrade prompt message and UI materials. 2. Signal loss prompt (estimated 4 days) 3. Firmware update process (estimated 9 days): It is not recommended to adjust the firmware update process. After the adjustment, all produced products can only be updated by disassembling them. Moreover, after adjusting this process, a significant amount of time is required for testing the function to ensure stability. If the firmware update fails, it can only remain at the upgrade interface because the previous program has been dele·ted and cannot be redirected. 4. Alarm/Camera Vehicle Report (estimated 6 days): There are currently 20 alarm IDs. Should they be handled differently for the camera vehicle, or should all others be processed according to Alert Reporting? Need to provide UI materials. 5. Dormant Alarm (estimated 4 days): Need to provide UI materials. 6. Reset Processing (estimated 4 days): Need to provide UI materials. 12.06.25 Updated UI and protocol submitted on 11.06.25 17.06.25 Updates sent by Nilesh on 17.06.25, please provide ETA. 01.07.25 1. Implemented 2. Implemented 3. Implemented 4. Implemented 5. Not Implemented Correctly, “Do not turn off” text are missing. Please refer EES_Firmware_Task_TrackerV1.4.pdf i sent. Question: Can we upgrade only Main Firmware from app? What if we need to upgrade UI and Audio firmware via Application? 6. Issue with mute button, it should not hide alert, that button is just to mute audio. Please find video in Lark 7. Issue with mute button, it should not hide alert, that button is just to mute audio. Please find video in Lark 8. After alert is dismissed and you press Left to add new Alert, instead of New Alert it shows Report Alert. Please find video in Lark. 9. Implemented 10. Factory Reset not working while device is not connected. Please find video in Lark 11. Setup complete Screen is not appearing after successful pairing. Please find video in lark. 12. Firmware version for Audio is not receiving. | 设备更新： 1、无意义，更新的确认与下载，应在APP中操作，无需在设备中重复操作 2、该操作导致业务逻辑复杂化，延长开发时间 3、设备与APP通讯中为从设备，该逻辑违反当前通讯模式 GPS提示： 无意义，旁边图标已明显提示 Equipment Update: 1. This is meaningless. The confirmation and download of updates should be performed in the APP, and there is no need to repeat the operation on the device. 2. This operation complicates the business logic and prolongs the development time. 3. In the communication between the device and the APP, the device is the client. This logic violates the current communication mode. GPS Notification: This is meaningless. The adjacent icon provides a clear indication. 05.06.25[新需求] 1、UI添加升级提示（预估需6天）:需明确触发哪个按钮进入“升级提示”界面，提供升级提示报文、UI素材 2、信号弃失提示（预估需4天） 3、固件更新流程（预估需9天）: 不建议调整固件更新流程，调整后所有生产的产品只能拆开后更新。且调整该流程后需大量时间用于测试该功能，保证稳定。 固件更新失败只能停留在升级界面，因为之前的程序已经删除，不能跳转 4、报警/摄像车报告（预估需6天）： 当前共有20个报警ID，是否除摄像车特殊处理，其它都按Alert Reporting 处理？ 提供UI素材 5、休眠报警（预估需4天）：提供UI素材 6、重置处理（预估需4天）：提供UI素材 17.06.25 Need to provide some new UI material as discussion in Feishu Chat Group. 03.07.25 5. Not Implemented Correctly, “Do not turn off” text are missing. Please refer EES_Firmware_Task_TrackerV1.4.pdf i sent. Question: Can we upgrade only Main Firmware from app? What if we need to upgrade UI and Audio firmware via Application? EES:"Do not turn off"已添加，但需要重新寄新设备才能看到，由于boot程序空间限制，"Firmware updated"和图标 ✔ 不能做进去 6. Issue with mute button, it should not hide alert, that button is just to mute audio. Please find video in Lark EES:已更改 7. Issue with mute button, it should not hide alert, that button is just to mute audio. Please find video in Lark EES:已更改 8. After alert is dismissed and you press Left to add new Alert, instead of New Alert it shows Report Alert. Please find video in Lark. EES:没发现此现象，请使用最新的固件测试 9. Implemented 10. Factory Reset not working while device is not connected. Please find video in Lark EES：已更改 11. Setup complete Screen is not appearing after successful pairing. Please find video in lark. EES:已更改为停留3秒 12. Firmware version for Audio is not receiving. EES: 由于批量音频程序已经烧录好，无法增加版本号
6 | Compass Icons Not Correct | Compass icon shows incorrect orientation; red dot should point to true north. | Firmware adjustment by EES | New release 22 May will fix 30.05.25 The app is sending the correct heading values. Please share the logic you have implemented on the device to handle the heading data so we can verify and ensure consistency. 09.06.25 Correct logic should be N 337.5° – 22.5° NE 22.5° – 67.5° E 67.5° – 112.5° SE 112.5° – 157.5° S 157.5° – 202.5° SW 202.5° – 247.5° W 247.5° – 292.5° NW 292.5° – 337.5° 12.06.25 Verified this issue, it is fixed now | Picture 1和3方向与红点大致对应，Picture2 都有异常 建议：APP发送CurrentHeading数据，每秒加1，从0~359循环测试，查看红点是否正确（0为正上方） Picture 1 and Picture 3 are roughly aligned with the red dot. Picture 2 shows abnormalities. Suggestion: The APP should send the "CurrentHeading" data, incrementing by 1 every second, and conducting a cycle test from 0 to 359 to check if the red dot is correct (0 represents the top). 05.06.25[问题] 更新V00.1.4 0红点指向正上，90红点指向正右，180红点指向正下，270红点指向正左 [bug] 0: Red dot points upwards; 90: Red dot points to the right; 180: Red dot points downwards; 270: Red dot points to the left. 10.06.25 更新V00.1.6 根据提供图片信息调整逻辑 Updated FW to V00.1.6 Adjust the logic based on the information provided in the picture.
7 | Sounds for Smart Motorways | Add missing alert sounds for Smart Motorway alerts. | The sound playback is controlled by the APP.Pls check APP(ID:0x09,[0]~[2]) | John to resend sounds. 30.05.25 1. The WelcomePure sound is already part of the existing protocol and is currently played when the device is powered on. For the Sync device, it should instead play the WelcomeSync sound. Both the sound file and protocol have already been updated to support this. 09.06.25 We will send missing sound for Dutch. 12.06.25 Missing sound are sent. 17.06.25 On Start up it should say Welcome Sync. 01.07.25 Verified this issue, it is fixed now | 接收到额外语音文件。 飞书群中沟通，还缺少“WelcomePure”音频文件 措施：确保语音文件完整后，更新固件 注意：语音调整，会影响设备出厂。每台设备更新语音包需要7分钟 Received additional audio file. Communication within the Feishu group still lacks the "WelcomePure" audio file. Measures: Ensure the audio file is complete before updating the firmware. Note: Audio adjustment will affect the factory settings of the device. Each device requires 7 minutes for the audio package update. 05.06.25[新需求] 确保音频文件完整（预估需2天） [new requirement] Ensure to provide completed audio file to EES (then estimated to take 2 days) 10.06.25 Finish by 13th, June. 17.06.25 Finished.
8 | Upcoming Speed Not Displayed | Upcoming speed limit changes are not shown on the device display. | More specific descriptions or pictures are needed. | EES to update FW when receive new UI files/figma 30.05.25 A detailed description of this behavior has been provided under Task 8. Kindly review it for further clarification. 09.06.25 We will test once we will receive new firmware. 12.06.25 Verified this issue, it is fixed now | 显示20是该ui对应报警ID20中的tup 该问题与第三点类似，需沟通清楚各数据所对应的UI 是否类似为右边图示，需说明清楚 Display 20 represents the tup in the alarm ID 20 of this UI. This issue is similar to the third point. It is necessary to communicate clearly about which UI corresponds to each piece of data. Is it similar to the illustration on the right? It is necessary to explain it clearly. Need Rushabh to provide new UI files. 05.06.25[新需求] 更新V00.1.6 [new requirement] Updated FW to V00.1.6
9 | Compass Link Visibility | Compass should disappear when not moving more than 8 km/h (requires app + firmware change). | More specific descriptions or pictures are needed. | EES to implement in FW 30.05.25: Can you please confirm if this behavior has been addressed in the firmware modifications made by EES? 09.06.25 We will test once we will receive new firmware. 12.06.25 Verified this issue, it is fixed now | 措施：固件调整 EES modified FW. 05.06.25[新需求] 更新V00.1.5 [new requirement] Updated FW to V00.1.5
10 | Button Logic Implementation | Implement button behavior as per shared specification document. | More specific descriptions or pictures are needed. | Rushabh will resend in Figma for EES to implement. 30.05.25: Waiting for Jon’s confirmation, we will send details soon. 09.06.25 Rushabh to send new material by 10.06.25 12.06.25 Submitted on 11.06.25 01.07.25 Verified this issue, it is fixed now | 未收到相关资料 No relevant materials have been received till 10th June. 17.06.25 Will upgrade with UI FW together by 2nd July.
11 | BT Serial Number | Display or communicate Bluetooth serial number from device. Proper Serial number should be part of advertisement data as well | The current BT module is not supported. | Davis will send explanatin including BT supplier opinion by reply to IPI/Rushabh/Jon Morgan & team 30.05.25: Using the serial number as the Bluetooth name should be acceptable and is aligned with standard device identification practices. 09.06.25 We will test once we will receive new firmware 12.06.25 EES to Provide tool to assign correct serial number to device. 17.06.25 While mass production how serial number will be assigned? 01.07.25 Waiting from EES | Regarding the BT serial number broadcast, the current Bluetooth module broadcast cannot store the complete serial number. The current complete serial number is Pure Sync - PS112500111106. The current Bluetooth broadcast name is Pure Sync - 0000. A feasible solution is to abandon 'Pure Sync - ' and adjust the Bluetooth name to PS112500111106. 05.06.25[问题] 更新V00.1.6 [bug] Updated FW to V00.1.6 17.06.25 Done in Feishu Chat Group.
12 | Firmware Upgrade | Device should support firmware upgrade from the application | Check the APP, and the device supports firmware upgrade. | Rushabh to verify protocol & test in 22 May FW 01.07.25 Question: Can we upgrade only Main Firmware from app? What if we need to upgrade UI and Audio firmware via Application? | 03.07.25 更新UI和音频固件与更新MCU固件方式相同，都是通过0x30/0x31指令进行更新
13 | Device UI turned off sometimes | Device stays connected but display does not update, this happens sometimes when device is idle and app reconnects |  | 30.05.25: 1. This is a bug. After establishing a connection, the device should automatically begin displaying the interface. Requiring the user to long press to wake up the device is not acceptable and should not be part of the user flow 01.07.25 Verified this issue, it is fixed now | 关屏状态下，设备蓝牙是正常打开，且允许连接，长按打开会自动跳转到主界面。(连接并不会唤醒设备) When the screen is off, the device's Bluetooth is normally on and allows connections. Long-pressing to open it will automatically switch to the main interface. (Connecting will not wake up the device.) 05.06.25[新需求] （预估需3天） [new requirement] Updated FW, estimated to take 3 days. 17.06.25 Will upgrade with UI FW together by 2nd July.
14 | Sound playback command does not work sometimes | Device does not play sound while sending sound playback command successfully, it seems race condition with sync command and sound command does get ignored |  | 30.05.25: This appears to be a bug. When the app sends a sound command while the sync command is in progress, the firmware is not consistently able to play the sound. This issue needs to be investigated further to ensure reliable sound playback during synchronization. 09.06.25 We did verify in the app, while sending sync command, in between if we send Sound Playback command device does not play it sometimes. This is bug in device firmware. Please test from your debug app as well. 01.07.25 Verified this issue, it is fixed now | 声音指令包含语音包更新，视频中操作可能触发语音包更新，更新语音包时禁止播放语音 建议：使用该指令前，先使用指令0x13获取声音配置信息 The voice command includes voice package update. The operation in the video may trigger the update of the voice package. When updating the voice package, playing of the voice is prohibited. Suggestion: Before using this command, first use command 0x13 to obtain the sound configuration information. 05.06.25 Need to solve this problem during App development by Iottive. 10.06.25 Per discussion by Feishu Chat, need Rushabh team to support verification and solving.
15 | Device does not store sounds settings | Device does not store sound settings from app, when app sends male to female, upon restart device does not play welcome message in female sound. When app turn off sounds, upon restart device still plays sound. |  | 17.06.25 Device should store all the parameters and upon start up please use those sound parameters. Consider if user has changed to Female, on Start up it should say Welcome message in Female voice. If use has disabled Audio playback on Start up device should not play any Welcome Message. 01.07.25 Verified this issue, it is fixed now | 17.06.25 语音变更后（男女声切换、国家切换），设备将更新语音芯片语音文件，需要20秒左右。（设置界面下，更新语音时，LED将白色呼吸） 关闭声音仍播放语音，请检查设置指令是否正常下发 After the voice change (switching between male and female voices, or between different countries), the device will update the voice chip's voice files, which takes about 20 seconds. (During the update in the settings interface, the LED will breathe in white.) If the voice is still playing when the sound is turned off, please check if the setting instructions were sent properly.
16 | Pairing Priority Not working | When there are two phones paired with single Pure Sync device and both phones are in range of Pure Sync device. Device allows connection with both phones and communication happens from both phones. Even if we change pairing priority communication happens from both phones. |  |  | 03.07.25 使用EES的测试APP，测试未发现此问题，请核对下优先级别0x08指令是否正确？ 22.08.25 1.优化蓝牙模组程序 2.优化控制板程序 3.APP连接指令需要有重发机制，否则那在多台手机同时连接时会出现有些手机连不上问题，这种情景当多台手机已经连接到Pure Sync后，Pure Sync断电后再上电，就很容易导致有些手机连接不上Pure Sync
17 | 配对页面超时30秒处理 | 在这页面增加30秒后退出到 Connecting to your paired..... |  |  | 22.08.25 1.已更改
18 | Meters无法显示4位数 |  |  |  | 22.08.25 1.已更改为可显示4位数
19 | S/N在断电,上电后有概率改变为程序初始值 |  |  |  | 04.09.25 1.已更改，用户设置和S/N保存区域分开
20 | 切换声音时断电后语音变为沙沙声 |  |  |  | 04.09.25 1.已更改，上电时若检测到语音文件不完整，立即把语音文件重新拷贝到语音IC中
21 | 屏幕在黑夜还时太亮 |  |  |  | 04.09.25 1.已更改，调低最低档亮度
22 | 固件更新失败可恢复到原来版本 |  |  |  | 06.09.25 1.已更改，需要使用新寄的三台机子，在更新固件状态显示如下：
21 | UI流程的更改 |  |  |  | 22.09.25 1.已更改
22 | 主页面UI的更改 |  |  |  | 24.09.25 1.已更改
23 | Current QR code is taking user to webpage to download app (Action: new QR is needed) |  |  |  | 25.09.25 已更改
24 | Pairing successful message is wrong, it is showing pairing_successful |  |  |  | 25.09.25 已更改
25 | Intelligent mute icon is wrong on top bar |  |  |  | 26.09.25 已更改
26 | Confirm Add new alert timeout is too short |  |  |  | 不用改
27 | Alert Mute Logic is still wrong - this appears to work correctly when top bar is visible. |  |  |  | 25.09.25 已更改
28 | Pairing Failed message space is missing after , |  |  |  | 25.09.25 已更改
29 | Report Alert timeout is too short |  |  |  | 不用改
30 | Subscription expired QR screen is taking user to pairing again |  |  |  | 25.09.25 已更改
31 | Subscription expired screen does not reset to normal after renew |  |  |  | 25.09.25 已更改
32 | Once Subscription expired screen is being displayed, device is removing pairing information |  |  |  | 25.09.25 已更改
33 | Pressing left button on connection screen does not reboot device |  |  |  | 25.09.25 已更改
34 | Factory reset is not working on pairing screen - it only works when device is connected to phone. |  |  |  | 25.09.25 已更改
35 | SmartMotorway Variable Speed UI is not implemented |  |  |  | 25.09.25 已更改
36 | Cloud connectivity UI is not implemented |  |  |  | 25.09.25 已更改
37 | When Top bar is hidden and if we press button, it displays top bar first and user needs to perform action again to change something |  |  |  | 25.09.25 已更改
38 | Firmware Update view timeout is too short |  |  |  | 不用改
39 | Pressing Left on firmware update asking user to follow the instructions in the app |  |  |  | 不用改
40 | Device does not auto connect in many cases
41 | When top bar is hidden, GPS Lost and Signal Lost messages are not coming |  |  |  | 25.09.25 已更改
42 | Button for reporting alert errors should be orange and left button. Instead it is orange and right button. |  |  |  | 25.09.25 已更改
43 | 12 hr clock. IT 4.45 in afternoon should be 4:45P. 04:45 is incorrect for 12H clock. A leading zero is required for 24H clock and should never be in 12H clock. |  |  |  | 已更改
44 | METER should be spelled METRE |  |  |  | 25.09.25 已更改
45 | Compass, please check position of red dot against Figma. |  |  |  | 25.09.25 已更改
46 | 橙色灯显示和绿色灯显示改到左边 |  |  |  | 27.09.25 已更改
47 | APP playback时可更改音量 |  |  |  | 27.09.25 已更改
48 | 没连接云的图标显示 |  |  |  | 27.09.25 已更改
49 | 指南针红点显示方位错误 |  |  |  | 30.09.25 已更改
50 | 在警报时声音按键逻辑错误 |  |  |  | 1.10.25 已更改
51 | 更改智能静音图标 |  |  |  | 1.10.25 已更改
52 | 开机欢迎由Welcome pure sync改为Welcome pure |  |  |  | 3.10.25 已更改
53 | 增加蓝牙广播厂家标识(0F81) |  |  |  | 17.10.25 已更改
53 | 恢复出厂设置显示不全 |  |  |  | 17.10.25 已更改
54 | 顶部菜单声音图标逻辑更改 |  |  |  | 14.11.25 已更改
55 | 顶部声音图标和右边栏声音图标不同步的问题 |  |  |  | 28.11.25 已更改
56 | 智能静音无法发出声音的问题 |  |  |  | 28.11.25 已更改
57 | 兼容TN屏和IPS屏 |  |  |  | 26.12.25 已更改
58 | 在固件请求更新倒计页面，增加用户按下左键后发送按键ID 0x30指令 |  |  |  | 26.01.26 已更改
59 | 速度限制显示按照右图进行显示 |  |  |  | 26.03.02 已更改
60 | QR Code Generation | Requirements: QR must be generated at runtime. QR must encode the full onboarding URL. QR must regenerate: On device boot After factory reset QR version level must support full URL length. Error correction level minimum: Medium (or as agreed). Performance Constraint: QR generation must not delay boot process beyond 500ms. Must not block BLE stack initialization. |  |  | 26.04.20 已更改
61 | Simplified Pairing Process |  |  |  | 26.04.20 已更改
62 | Advertising Data |  |  |  | 26.04.20 已更改
63 | Support for New Alerts (Danger Zone & Dangerous Intersection) |  |  |  | 26.04.20 已更改
64 | 更改二维码地址 |  |  |  | 26.05.11 已更改
65 |  |  |  |  | 26.05.29 已更改
66 | 解决智能静音，按了静音后还会报声音的bug |  |  |  | 26.06.22 V01.2.4 已更改
67 | 去掉扫描二维码的顶部文字显示和"序列号" |  |  |  | 26.06.22 V01.2.5 已更改 注意：FW-PureSync-Main-APP-V1.2.5(FD9C0432).bin和FW-PureSync-UI-V01.0.8(138979CD).bin需要同步更新，否则会出现UI显示混乱
Current document version record
| UI | http://figma.com/design/ppDZ8aUBOsBYbIxoRQu2yQ/Pure-Sync-UI
| Protocol | Pure Sync Bluetooth Protocol V2_20250526
Device software version
| 序号 | 问题 | 状态 | 测试结果
| 1 | Current QR code is taking user to webpage to download app (Action: new QR is needed) | 已更改
| 2 | Pairing successful message is wrong, it is showing pairing_successful | 已更改
| 3 | Intelligent mute icon is wrong on top bar | 已更改
| 4 | Confirm Add new alert timeout is too short | 不用改
| 5 | Alert Mute Logic is still wrong - this appears to work correctly when top bar is visible. | 已更改
| 6 | Pairing Failed message space is missing after , | 已更改
| 7 | Report Alert timeout is too short | 不用改
| 8 | Subscription expired QR screen is taking user to pairing again | 已更改
| 9 | Subscription expired screen does not reset to normal after renew | 已更改
| 10 | Once Subscription expired screen is being displayed, device is removing pairing information | 已更改
| 11 | Pressing left button on connection screen does not reboot device | 已更改
| 12 | Factory reset is not working on pairing screen - it only works when device is connected to phone. | 已更改
| 13 | SmartMotorway Variable Speed UI is not implemented | 已更改
| 14 | Cloud connectivity UI is not implemented | 已更改
| 15 | When Top bar is hidden and if we press button, it displays top bar first and user needs to perform action again to change something | 已更改
| 16 | Firmware Update view timeout is too short | 不用改
| 17 | Pressing Left on firmware update asking user to follow the instructions in the app | 不用改
| 18 | Device does not auto connect in many cases
| 19 | When top bar is hidden, GPS Lost and Signal Lost messages are not coming | 已更改
| 20 | Button for reporting alert errors should be orange and left button. Instead it is orange and right button. | 已更改
| 21 | 12 hr clock. IT 4.45 in afternoon should be 4:45P. 04:45 is incorrect for 12H clock. A leading zero is required for 24H clock and should never be in 12H clock. | 已更改
| 22 | METER should be spelled METRE | 已更改
| 23 | Compass, please check position of red dot against Figma. | 已更改

## Version Control
Table 1
Version | Who | Reason